AISA  /  POWER PLATFORM

Delivery & Release

Process

A traceable path from intake to production operation and retirement

| DOCUMENT | PP-PRO-001 |
| --- | --- |
| STATUS | Draft for organisational approval |
| VERSION | 1.0 |
| EFFECTIVE | 3 September 2026 |
| OWNER | Engineering Delivery Lead |
| APPROVER | Power Platform Service Owner |
| REVIEW | Every six months |

CONTROLLED DOCUMENT Review named authorities, risk thresholds, service levels, retention requirements and volatile platform behaviour before approval.

# How to use this document

This document is a draft governance instrument derived from the canonical Power Platform evidence set. It becomes binding only after approval through the organisation’s document-control process.

| Term | Interpretation |
| --- | --- |
| MUST / MUST NOT | Mandatory requirement |
| SHOULD / SHOULD NOT | Expected; deviation requires recorded justification |
| MAY | Optional within the stated boundaries |

EVIDENCE HANDLING UNKNOWN, CONFLICTED, INF and VOLATILE VALUE evidence must retain its canonical meaning and must not be silently converted into a fixed rule.

# Delivery lifecycle

| 01 INTAKE | Record purpose, users, data, criticality, licensing and support expectations. |
| --- | --- |
| 02 DESIGN | Approve environment, solution boundary, identity, security, recovery and operating model. |
| 03 BUILD | Develop in an approved environment against source-controlled work items. |
| 04 VALIDATE | Run peer, static, dependency, functional, security and material performance checks. |
| 05 PROMOTE | Create a managed artifact and deploy through the approved pipeline. |
| 06 VERIFY | Smoke-test identity, connections, monitoring and business operation. |
| 07 OPERATE | Transfer ownership, support, runbooks, known limits and recovery procedures. |
| 08 RETIRE | Approve shutdown, handle data, remove access and update the inventory. |

# Release gates

| Gate | Minimum evidence | Accountable outcome |
| --- | --- | --- |
| Architecture ready | Approved design and classification | Build may begin |
| Build ready | Reviewed change linked to work | Artifact may be created |
| Test ready | Deployable artifact and test plan | Controlled validation begins |
| Production ready | Controls, acceptance and support readiness | Release is authorised |
| Release complete | Smoke test, monitoring and release record | Service is operational |

# Production rules

| MUST NOT | Direct authoring occurs in production unless emergency access is invoked. |
| --- | --- |
| MUST | The deploying identity and resulting component ownership are intentional and documented. |
| MUST | Environment values and connection bindings are supplied per target. |
| MUST NOT | A release claims instant rollback unless the exact method has been tested. |
| MUST | Failures follow the documented incident, restore, redeploy, forward-fix or reconciliation path. |

# Evidence basis

The policy wording synthesises the following internal research artifacts. References are repository-relative; source status and reservations remain governed by the canonical manifest.

- Canonical manifest — research/pp/evidence/canonical-manifest.md

- Governance evidence — research/pp/evidence/governance.md

- Security evidence — research/pp/evidence/security.md

- ALM / DevOps evidence — research/pp/evidence/alm-devops.md

- Operations and support evidence — research/pp/evidence/operations-support.md

- Anti-pattern evidence — research/pp/evidence/anti-patterns.md

# Approval record

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Document owner |  |  |  |
| Security / architecture reviewer |  |  |  |
| Approver |  |  |  |